{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"defined_names":2},"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":7,"n_cols":33,"rows_kept":7,"merged":[[0,0,0,32],[1,0,3,0],[1,1,3,1],[1,2,3,2],[1,3,3,3],[1,4,3,4],[1,5,3,5],[1,6,3,6],[1,7,1,8],[1,9,3,9],[1,10,3,10],[1,11,3,11],[1,12,1,19],[1,20,1,21],[1,22,1,23],[1,24,3,24],[1,25,3,25],[1,26,3,26],[1,27,3,27],[1,28,3,28],[1,29,3,29],[1,30,3,30],[1,31,3,31],[1,32,3,32],[2,7,3,7],[2,8,3,8],[2,12,3,12],[2,13,3,13],[2,14,2,17],[2,18,3,18],[2,19,3,19],[2,20,3,20],[2,21,3,21],[2,22,3,22],[2,23,3,23],[4,0,4,2]]}
["泽州县2025年8月第二批衔接项目资金支出明细表"]
["序号","项目\n编码","项目名称","建设性质","项目类别","二级\n项目类型","项目\n子类型","建设任务",null,"实施地点","责任单位","项目行业\n主管部门","项目资金规模（元）",{"$nulls":7},"资金支出（元）",null,"实施期限",null,"项目总体\n绩效目标","联农带农\n机制","是否\n到户类","是否\n易地扶贫\n搬迁后扶\n项目","是否\n劳动密集型产业","是否\n采用以工\n代赈方式","是否\n招投标","是否\n形成资产","备注"]
[{"$nulls":7},"主要建设\n规模与内容","补助标准",{"$nulls":3},"项目投资\n概算","衔接资金\n合计","其中",{"$nulls":3},"其他\n财政资金","自筹\n资金","累计支出","本次支出","计划\n开工\n日期","计划\n完工\n日期"]
[{"$nulls":14},"中央","省级","市级","县级"]
["合计",{"$nulls":11},{"$f":"SUM(M6:M7)","v":{"v":443800,"d":"443800.00"}},{"$f":"SUM(N6:N7)","v":395667.72},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},395667.72,{"v":0,"d":"0.00"},48132.28,{"v":304500,"d":"304500.00"},91167.72]
[1,"5100001587442950"," 2025年高都镇大兴（小丰头自然村）保障管网改造项目","新建","乡村建设行动","农村基础设施（含产业配套基础设施）","农村供水保障设施建设","新建阀门房、排气阀门井、水表井，安装水表及配件等","— —","大兴村","高都镇人民政府","县水务局",428800,380667.72,0,0,0,380667.72,0,{"$f":"M6-N6","v":48132.28},304500,76167.72,202503,202511,"新建阀门房、排气阀门井、水表井，安装水表及配件等","巩固饮水安全","否","否","否","否","是","否"]
[2,"5100001587344904"," 2024-2025学年雨露计划","新建","巩固三保障成果","教育","享受“雨露计划”职业教育补助","通过开展雨露计划补助项目，达到减轻脱贫户经济压力。","3000元/生","泽州县","泽州县乡村振兴中心","县乡村振兴中心",15000,15000,0,0,0,15000,0,0,0,15000,202503,202511,"通过开展雨露计划补助项目，达到减轻脱贫户经济压力。","教育补助","否","否","否","否","否","否"]